## Sheet1
HAVERFORDWEST PROPOSED INM SCHEMES
REF. | SCHEME | EASTING | NORTHING | NEW | UPGRADE | FOOTWAY | FOOTPATH | CROSSING | SUP | OTHER | S/M/L Term | LAND OWNERSHIP | COSTINGS | ECOLOGICAL ISSUES
INMHW1 | Merlins Bridge - Clay Lane - Pedestrian Passing Areas-Winch Lane | 195638 | 214414 | X | [5 empty] | X | M | Land Required
INMHW2 | Merlins Bridge Traffic Signalled Roundabout - Lengthen Pedestrian Phases | 194713 | 214561 |  | X |  |  |  |  | X | L | No Land Required
INMHW3 | Rifleman's Field - St Thomas Green - (Upgrade existing crossing to zebra) - Church Lane | 195279 | 215322 |  | X |  |  | X |  |  | M | No Land Required
INMHW5 | Scarrowscant Lane on road cycle route signing | 194055 | 214735 | X | [6 empty] | M | No Land Required
INMHW7 | Goshawk Road - St Davids Road -Thomas Parry Way - Shared use path link with crossing | 194369 | 215957 | X |  |  |  | X | X |  | S | Land Required | £40k
INMHW8 | Haroldston Terrace Merlins Bridge - Widen Footways/Priority System | 194768 | 214485 |  | X | X |  |  |  |  | L | No Land Required
INMHW9 | A40 TR Controlled Crossing outside Aldi connecting to New Road | 195818 | 215692 |  | X |  |  | X |  |  | L | Land Required
INMHW10 | Quay Street / Union Hill / Clay Lane - visibility improvements and footway improvement | 195595 | 215118 |  | X |  |  |  |  | X | M | Land Required
INMHW11 | Avallenau Drive to Haylett Lane - Footpath Link | 194726 | 214197 | X |  |  | X |  |  |  | M | Land Required
INMHW12 | Picton Place - Traffic Control Junction - Faster response to pedestrian crossing request | 195607 | 215720 |  | X |  |  |  |  | X | S | No Land Required | £2k
INMHW13 | Fishguard Road -Withybush Hospital - Retail Park - Footway Link | 195762 | 216754 | X |  | X |  | X |  |  | M | Land Required
INMHW14 | Crowhill Road - Cashfields to Northgate - Footway Link to St Martins Park and dropped kerb crossing | 195225 | 216222 | X |  | X |  | X |  |  | M | No Land Required
INMHW15 | North Crescent - Pedestrian improvements | 195146 | 216027 | X |  | X |  |  |  |  | M | Land Required
INMHW16 | Crundale - footways and associated traffic calming | 196739 | 217832 | X | [5 empty] | X | M | Land Required
INMHW17 | Crundale to Withybush industrial estate - footpath. | 196677 | 218195 | X |  |  | X |  |  |  | M | Land Required
INMHW19 | Withybush Road Roundabout to Cardigan Road Roundabout - Shared use paths and crossings | 196097 | 217336 | X |  |  |  |  | X |  | S | No Land Required (Trunk Road?) | £220k
INMHW20 | Scotchwell Walk to Sir Thomas Picton School - improve footpaths | 195850 | 215784 |  | X |  | X |  |  |  | M | No Land Required (PCC Land + PROW)
INMHW21 | Haverfordwest to Uzmaston - Shared use path. Link to continue to Narberth | 196077 | 215131 |  | X |  |  |  | X |  | L | Land Required |  | Protected species
INMHW22 | Castle Lake Car Park to Castle Square - Pedestrian link path | 195381 | 215679 | X |  |  | X |  |  |  | S | Land Required | £156K
INMHW23 | Withybush Roundabout to Ridgeway Retail Park - Shared use path | 195800 | 217643 | X |  |  |  |  | X |  | L | Land Required (Trunk Road?) |  | Verge /Hedges
INMHW24 | Pembrokeshire College - Brooklands Park- Scarrowscant Lane - Shared use path and cycle route | 194345 | 214539 | X |  | X |  |  |  |  | M | Land Required
INMHW25 | Cardigan Road to Prendergast School via Tan Bank footway and dropped kerbs | 195953 | 216437 |  | X |  | X |  |  |  | S | Land Required | £50k
INMHW26 | County Hall -Picton Place alongside river to pedestrian footbridge - improve footpath | 195515 | 215730 |  | X |  | X |  |  |  | M | No Land Required |  | Protected site
INMHW29 | Ashford Lane Crundale to Rosemary Lane footpath | 196692 | 218133 | X |  |  | X |  |  |  | M | Land Required
INMHW30 | City Road Barn Street area crossing facility | 195197 | 215775 | X |  | X |  | X |  |  | S | No Land Required
* | Cycle parking at appropriate locations |  |  | X | [5 empty] | X
* | Pedestrian signing scheme distance and time |  |  | X | [5 empty] | X
* | Proposals as a result of consultations not included in the Integrated Network Map at this stage but to be further investigated